## Overview
HealthAccess - Stakeholder Status Report
Generated 2026-09-03 08:13 UTC ¦ matdevstamp/inl-3-awesome-journal
Summary
Metric | Planned | Open | Closed | Blocked | Overdue | Unassigned
Count | 17 | 4 | 0 | 3 | 0 | 20
Epics (by Gate)
Epic (Gate) | Tasks | Planned | Open | Closed | Blocked | Overdue | Unassigned | Next deadline
1-Decisions | 3 | 0 | 3 | 0 | 2 | 0 | 2 | 2026-09-04
2-Scaffold | 7 | 6 | 1 | 0 | 1 | 0 | 7 | 2026-09-05
3-Features | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 2026-09-16
4-Integration | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2026-09-23
5-Delivery | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 2026-09-29
Streams (ownership)
Stream | Tasks | Planned | Open | Closed | Blocked | Overdue | Next deadline
A-Identity | 2 | 2 | 0 | 0 | 0 | 0 | 2026-09-16
B-Patient | 1 | 1 | 0 | 0 | 0 | 0 | 2026-09-18
C-Notes | 1 | 1 | 0 | 0 | 0 | 0 | 2026-09-18
D-Audit | 2 | 2 | 0 | 0 | 0 | 0 | 2026-09-16
Other | 15 | 11 | 4 | 0 | 3 | 0 | 2026-09-04

## Changelog
Changelog - changes since the previous export
Compared against the snapshot of 2026-09-03 08:12 UTC
Sheet | Task | What changed | Before | After
No changes since the previous export.

## Tasks
Key | Epic (Gate) | Stream | Title | State | Assignee | Deadline | Effort | Blocked by | Related | GitHub | Open questions
01 | 1-Decisions |  | Project Setup & Group Contract | Open | Team | 2026-09-04 | 2h |  |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/1 | 4
02 | 1-Decisions |  | Database Choice Discussion | Open | Team | 2026-09-04 | 1h (meeting) | #1 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/2 | 4
03 | 1-Decisions |  | Graphify Architecture Artifacts | Open | Scaffold pair (Person 1 + Person 2) | 2026-09-05 | 2h | #1, #2 | 20 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/3 | 1
04 | 2-Scaffold |  | Database Design & Setup | Open | TBD | 2026-09-05 | 4h | #1, #2, #3 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/4 | 4
05 | 2-Scaffold |  | Vite + Tailwind CSS + shadcn/ui Setup | Planned | TBD | 2026-09-05 | 3h | #1, #3 |  |  | 3
06 | 2-Scaffold |  | Backend Project Setup | Planned | TBD | 2026-09-06 | 4h | #4, 05 |  |  | 3
07 | 2-Scaffold |  | TypeScript Strict Configuration | Planned | TBD | 2026-09-06 | 2h | 05, 06 |  |  | 3
08 | 2-Scaffold |  | ESLint + Prettier Configuration | Planned | TBD | 2026-09-07 | 2h | 05, 07 |  |  | 3
09 | 2-Scaffold |  | Playwright E2E Testing | Planned | TBD | 2026-09-08 | 8h | 05, 06, 07, 08 | 10, 19 |  | 4
10 | 2-Scaffold |  | GitHub Actions CI/CD Workflow | Planned | TBD | 2026-09-08 | 3h | 05, 08, 07, 06 | 09 |  | 3
11 | 3-Features | A-Identity | Backend API & Authentication | Planned | TBD | 2026-09-16 | 8h | #4, 07, 06 |  |  | 4
12 | 3-Features | A-Identity | Frontend UI Development | Planned | TBD | 2026-09-16 | 12h | 05, 07, 06 |  |  | 4
13 | 3-Features | B-Patient | Patient View & Search | Planned | TBD | 2026-09-18 | 6h | #4, 11, 12 | 14 |  | 4
14 | 3-Features | C-Notes | Medical Notes with Visibility Control | Planned | TBD | 2026-09-18 | 5h | #4, 11, 12 | 13 |  | 4
15 | 3-Features | D-Audit | Blockchain Access Logging | Planned | TBD | 2026-09-16 | 8h | #4, 07, 06 | 18 |  | 4
16 | 3-Features | D-Audit | P2P Network Implementation | Planned | TBD | 2026-09-18 | 6h | 15, 06 |  |  | 4
17 | 4-Integration |  | User Roles & Access Control | Planned | TBD | 2026-09-23 | 6h | 11, 12, 13, 14 |  |  | 4
18 | 4-Integration |  | Socket.io Broadcasting | Planned | TBD | 2026-09-23 | 5h | 17, 14, 16, 12 | 15 |  | 4
19 | 5-Delivery |  | Testing & Quality Assurance | Planned | TBD | 2026-09-29 | 8h | 17, 15, 16, 18 | 09, 20 |  | 4
20 | 5-Delivery |  | Documentation & README | Planned | TBD | 2026-09-29 | 4h | #1 | #3, 19 |  | 4
21 | 5-Delivery |  | Presentation Preparation | Planned | Team | 2026-10-01 | 6h | 19, 09, 20 |  |  | 4

## Questions
Epic (Gate) | Task | Question | Resolved?
1-Decisions | 01 Project Setup & Group Contract | Which frontend framework will we use? (React, Vue, Svelte?) | No
1-Decisions | 01 Project Setup & Group Contract | Which authentication method? (JWT, sessions, passwordless?) | No
1-Decisions | 01 Project Setup & Group Contract | How will we handle the blockchain implementation? | No
1-Decisions | 01 Project Setup & Group Contract | What database will we use? (PostgreSQL, MySQL, SQLite?) | No
1-Decisions | 02 Database Choice Discussion | Which database do we choose? (SQLite, PostgreSQL, or both?) | No
1-Decisions | 02 Database Choice Discussion | How to handle the P2P requirement with the chosen database? | No
1-Decisions | 02 Database Choice Discussion | Should we use Docker for PostgreSQL in development? | No
1-Decisions | 02 Database Choice Discussion | How to handle database seeding? | No
1-Decisions | 03 Graphify Architecture Artifacts | Which graphify version and command will be documented in the README? | No
2-Scaffold | 04 Database Design & Setup | PostgreSQL vs SQLite? (see task 02-database-choice-discussion.md) | No
2-Scaffold | 04 Database Design & Setup | Should we use Prisma as the single source of truth? | No
2-Scaffold | 04 Database Design & Setup | How to handle database seeding? | No
2-Scaffold | 04 Database Design & Setup | Do we need indexes for this project scale? | No
2-Scaffold | 05 Vite + Tailwind CSS + shadcn/ui Setup | Which shadcn/ui components do we need initially? | No
2-Scaffold | 05 Vite + Tailwind CSS + shadcn/ui Setup | Should we use dark mode from the start? | No
2-Scaffold | 05 Vite + Tailwind CSS + shadcn/ui Setup | Custom color palette or default shadcn colors? | No
2-Scaffold | 06 Backend Project Setup | PostgreSQL vs SQLite for development? | No
2-Scaffold | 06 Backend Project Setup | Which ORM to use? (Prisma recommended) | No
2-Scaffold | 06 Backend Project Setup | Should we use a logger library (winston, pino)? | No
2-Scaffold | 07 TypeScript Strict Configuration | Should we enable `exactOptionalPropertyTypes`? | No
2-Scaffold | 07 TypeScript Strict Configuration | How to handle third-party library types? | No
2-Scaffold | 07 TypeScript Strict Configuration | Should we use `type` or `interface`? | No
2-Scaffold | 08 ESLint + Prettier Configuration | Should we use Biome instead of ESLint + Prettier? (faster) | No
2-Scaffold | 08 ESLint + Prettier Configuration | Which import sorting order do we prefer? | No
2-Scaffold | 08 ESLint + Prettier Configuration | Should we enforce strict TypeScript rules? | No
2-Scaffold | 09 Playwright E2E Testing | How to handle test data seeding? | No
2-Scaffold | 09 Playwright E2E Testing | Should we test on multiple browsers? | No
2-Scaffold | 09 Playwright E2E Testing | How to handle real-time test assertions? | No
2-Scaffold | 09 Playwright E2E Testing | Should we mock API calls or use real backend? | No
2-Scaffold | 10 GitHub Actions CI/CD Workflow | Should we deploy on merge to main? | No
2-Scaffold | 10 GitHub Actions CI/CD Workflow | Which hosting platform for deployment? | No
2-Scaffold | 10 GitHub Actions CI/CD Workflow | Should we run E2E tests in CI? | No
3-Features | 11 Backend API & Authentication | JWT vs session-based auth? (JWT recommended for simplicity) | No
3-Features | 11 Backend API & Authentication | Should we implement passwordless login? | No
3-Features | 11 Backend API & Authentication | How long should tokens be valid? | No
3-Features | 11 Backend API & Authentication | Should we use an API framework like Fastify instead of Express? | No
3-Features | 12 Frontend UI Development | React vs Vue vs Svelte? (React recommended) | No
3-Features | 12 Frontend UI Development | Which CSS framework? (Tailwind recommended) | No
3-Features | 12 Frontend UI Development | State management approach? (Context API vs Redux) | No
3-Features | 12 Frontend UI Development | Should we use a component library? (Material UI, Ant Design?) | No
3-Features | 13 Patient View & Search | How to handle Swedish characters in search? (å, ä, ö) | No
3-Features | 13 Patient View & Search | Should we implement autocomplete for search? | No
3-Features | 13 Patient View & Search | What's the optimal page size for search results? | No
3-Features | 13 Patient View & Search | Should we cache search results? | No
3-Features | 14 Medical Notes with Visibility Control | Should notes support rich text or plain text only? | No
3-Features | 14 Medical Notes with Visibility Control | What's the character limit for notes? | No
3-Features | 14 Medical Notes with Visibility Control | Should we show edit history for notes? | No
3-Features | 14 Medical Notes with Visibility Control | How to handle note deletion (soft delete vs hard delete)? | No
3-Features | 15 Blockchain Access Logging | Which blockchain library to use? (Consider crypto-js for simplicity) | No
3-Features | 15 Blockchain Access Logging | How to handle blockchain size growth? | No
3-Features | 15 Blockchain Access Logging | Should we implement mining/proof-of-work? (Probably not needed) | No
3-Features | 15 Blockchain Access Logging | How to handle server downtime and sync recovery? | No
3-Features | 16 P2P Network Implementation | How to handle server startup order? | No
3-Features | 16 P2P Network Implementation | What's the sync interval for blockchain? | No
3-Features | 16 P2P Network Implementation | How to handle conflicting updates? | No
3-Features | 16 P2P Network Implementation | Should we implement encryption for P2P messages? | No
4-Integration | 17 User Roles & Access Control | How to handle organization-based access for vårdcentral? | No
4-Integration | 17 User Roles & Access Control | Should we implement audit logging for all access attempts? | No
4-Integration | 17 User Roles & Access Control | How to handle role changes (e.g., nurse becomes doctor)? | No
4-Integration | 17 User Roles & Access Control | Should we implement session timeout? | No
4-Integration | 18 Socket.io Broadcasting | Should we use Redis adapter for scaling? | No
4-Integration | 18 Socket.io Broadcasting | How to handle socket authentication? | No
4-Integration | 18 Socket.io Broadcasting | What's the reconnection strategy? | No
4-Integration | 18 Socket.io Broadcasting | Should we implement message acknowledgments? | No
5-Delivery | 19 Testing & Quality Assurance | Which testing framework to use? (Jest recommended for Node.js) | No
5-Delivery | 19 Testing & Quality Assurance | How to set up test database? | No
5-Delivery | 19 Testing & Quality Assurance | Should we implement E2E tests with Cypress? | No
5-Delivery | 19 Testing & Quality Assurance | How to handle socket.io testing? | No
5-Delivery | 20 Documentation & README | Which screenshot tool to use? | No
5-Delivery | 20 Documentation & README | How detailed should API documentation be? | No
5-Delivery | 20 Documentation & README | Should we use a documentation generator (e.g., Swagger)? | No
5-Delivery | 20 Documentation & README | How to format meeting notes consistently? | No
5-Delivery | 21 Presentation Preparation | Will we use slides or just live demo? | No
5-Delivery | 21 Presentation Preparation | Who presents which part? | No
5-Delivery | 21 Presentation Preparation | What's the backup if demo fails? | No
5-Delivery | 21 Presentation Preparation | How to handle unexpected questions? | No